## Gantt Chart
TASK NUMBER | TASK TITLE | START DATE | DUE DATE | DURATION | TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Research Paper
1.1 | Research | 2021-02-01 | 2021-02-15 | 14 | 100% | bar: WEEK 1 M to WEEK 3 M
1.2 | High-Level Analysis | 2021-02-07 | 2021-02-17 | 10 | 100% | bar: WEEK 2 M to WEEK 3 W
1.3 | Detailed Analysis of Core Modules | 2021-02-12 | 2021-02-19 | 7 | 100% | bar: WEEK 2 F to WEEK 3 F
1.4 | Detailed Analysis of Supporting Modules | 2021-02-22 | 2021-02-25 | 3 | 100% | bar: WEEK 4 M to WEEK 4 R
2 | Comprehension Of Mathematicals Concepts & Algorithms
2.1 | Surface Represenation | 2021-02-26 | 2021-03-01 | 5 | 100% | bar: WEEK 4 F to WEEK 5 T
2.2 | Structure Represenation | 2021-03-02 | 2021-03-07 | 5 | 100% | bar: WEEK 5 W to WEEK 5 F
2.3 | Texture Represenation | 2021-03-05 | 2021-03-10 | 5 | 100% | bar: WEEK 5 F to WEEK 6 W
3 | Project Implementation
3.1 | Selection of Server Hosting | 2021-03-11 | 2021-03-12 | 1 | 100% | bar: WEEK 6 R to WEEK 6 F
3.2 | Configuration of Server | 2021-03-13 | 2021-03-16 | 3 | 100% | bar: WEEK 7 M to WEEK 7 T
3.3 | Development of Core Modules | 2021-03-17 | 2021-03-24 | 7 | 100% | bar: WEEK 7 W to WEEK 8 W
3.4 | Development of Supporting Modules | 2021-03-22 | 2021-03-30 | 8 | 100% | bar: WEEK 8 M to WEEK 9 T
3.5 | Quality Assurance of Core Modules | 2021-03-30 | 2021-04-04 | 4 | 100% | bar: WEEK 9 T to WEEK 9 F
3.6 | Quality Assurance of Supporting Modules | 2021-04-01 | 2021-04-06 | 5 | 100% | bar: WEEK 9 R to WEEK 10 M
3.7 | Collecting Dataset | 2021-04-07 | 2021-04-08 | 1 | 100% | bar: WEEK 10 T to WEEK 10 W
3.8 | Training Dataset | 2021-04-08 | 2021-04-10 | 2 | 100% | bar: WEEK 10 W to WEEK 10 F
3.9 | Building Pipeline | 2021-04-12 | 2021-04-19 | 7 | 100% | bar: WEEK 11 M to WEEK 12 M
3.1 | Creating API | 2021-04-15 | 2021-04-20 | 5 | 100% | bar: WEEK 11 R to WEEK 12 T
3.11 | Deployment | 2021-04-20 | 2021-04-23 | 3 | 100% | bar: WEEK 12 T to WEEK 12 F